## Main Board
DA VINCI PROJECT PLAN AND TASK BREAKDOWN
Phase | Task Name | Department | Assignee | Status | Duration | Start Time | Complete Time
X | JustPay landing page mockup re-design / 极付首页原型重新设计 | Product | Julie | Done | 1d | 2017-03-30 | 2017-03-30
| JustPay landing page UI re-design / 极付首页 UI 重新设计 | UI | Tony | Done |  | 2017-03-31
| JustPay landing page development / 极付首页页面开发 | Front-end | Xiaopeng | To-do | 1d | 2017-04-14
| Cancel invoke `notification.js` and `activity.js` / 取消调用`notification.js` 与 `activity.js` | Front-end | Xiaopeng | To-do
| Add JustPay notification bar / 添加极付通知条 | Front-end | Xiaopeng | To-do
| New user cannot see "My Wallet" button on landing page / 新用户于极付首页无法看到“钱包”按钮 | Front-end | Xiaopeng | To-do
| Front-end change of "receive bitcoin" page for new user without JustPay address / 无极付地址用户”接收比特币“页面前端修改 | Front-end | Xiaopeng | To-do
| Ban "allocate justpay address" api (update `wallet_tm` status) / 禁用"allocate justpay address" api | Back-end | Ninjia | Testing |  | 2017-03-31
| Send out "X" announcement email / 发送“X“通知邮件 | CSR
Y | Migration page mockup design / 迁移页面原型设计 | Product | Julie | Done | 1d | 2017-03-31 | 2017-03-31
| Migration page UI design / 迁移页面 UI 设计 | UI | Tony | To-do
| Page notification announcement / 页面通知条公告 | Product | Julie | To-do
| Homepage and inner page access to migration page / 首页与内页进入迁移页面入口 | Front-end | Xiaopeng | To-do | 1d | 2017-04-15
| Migration page / 迁移页面开发 | Front-end | Xiaopeng | To-do
| “verify user registration on mobi” api | Back-end | Chaochao | To-do | 2w | 2017-04-10
| "transfer justpay address to mobi" api | Back-end | Chaochao | To-do | 2w | 2017-04-10
| Provide "mobi registration" api / 判断是否注册 mobi api | Back-end | Ninjia | In-progress | 1d | 2017-04-11
| "verify user info" api (transaction pw, sms vcode, 2 factor) api | Back-end | Ninjia | In-progress |  | 2017-04-01
| Full justpay balance send to mobi address (onchain) / 所有极付余额发送至 mobi 地址 | Back-end | Ninjia | In-progress |  | 2017-04-01
| Add api to allow user to send if the amount exceeds 10 btc / 允许发送数额超过 10 BTC 的用户发送 api | Back-end | Ninjia | In-progress
| Add api to justify whether user has finished migration / 添加判断用户是否已迁移 api | Back-end | Ninjia | In-progress
| Send out "Y" announcement email / 发送”Y“通知邮件 | CSR
Z | One-time transfer page mockup design / 转账页面原型设计 | Product | Julie |  | 1d | 2017-04-10 | 2017-04-10
| One-time transfer page UI design / 转账页面 UI 设计 | UI | Tony
| Page notification announcement / 页面通知条公告 | Product | Julie
| Hide send/receive/redeem mint buttons / 隐藏发送、接收、提现 Mint 按钮 | Front-end | Xiaopeng
| Show send/receive/redeem mint buttons according to whitelist / 根据白名单显示发送、接收、提现 Mint 按钮 | Front-end | Xiaopeng
| One-time transfer page / 转账页面开发 | Front-end | Xiaopeng
| Whitelist (company justpay accounts) / 白名单（公司极付账户） | Back-end | Ninjia
| Ban "send/receive/redeem mint" api / 禁用"send/receive/redeem mint" api | Back-end | Ninjia
| Full justpay balance transfer to outside bitcoin address / 所有极付余额发送至外部比特币地址 | Back-end | Ninjia
N | Page notification announcement / 页面通知条公告 | Product | Julie
| Hide "one-click migration" and "one-time transfer" pages for N triggered users / N 已触发用户隐藏”一键迁移页面“与”转账页面“ | Front-end | Xiaopeng
| Change "blockchain confirmation" script / 修改”区块链确认“脚本 | Back-end | Ninjia

## Status
To-do
In-progress
Testing
Pending-release
Done

## Department
UI
Front-end
Back-end
Database
Mobi
CSR
Product

## Assignee
Ninjia
Tony
Apple
Julie
Mikael
Chaochao
Xiaopeng